## UI
Effort Estimates (Man-hours)
USER STORY DECSRIPTION | JIRA ID | HTML | [5 empty] | Comments
|  | Screen Name/Sub task/ Features/ Components | Complexity | Effort (In Hrs) | Resource | Planned Start Date | Planned End Date
|  | Requirement Understanding, Analyze and Design the module . Do effort estimation, Technical Discussion & get Clarification. | Medium | 5 | Vishwanath M | 2019-01-09 | 2019-01-09
|  | Setup Initial Project and Branch, | Medium | 5 | Vishwanath M | 2019-01-09 | 2019-01-10
Dashboard - Home Page |  | UI Layout | Low | 2 | Vishwanath M | 2019-01-10 | 2019-01-10
Dashboard - Home Page |  | Pending Requests | Medium | 5 | Vishwanath M | 2019-01-10 | 2019-01-10
Dashboard - Home Page |  | Availed Leaves | Simple | 3 | Vishwanath M | 2019-01-11 | 2019-01-11
Dashboard - Home Page |  | Regularization | Simple | 3 | Vishwanath M | 2019-01-11 | 2019-01-11
Dashboard - Home Page |  | Learning Hours | Simple | 3 | Vishwanath M | 2019-01-14 | 2019-01-14
Dashboard - Home Page |  | R-Samman | Simple | 3 | Vishwanath M | 2019-01-14 | 2019-01-14
Dashboard - Home Page |  | Manu Bar | Low | 2 | Vishwanath M | 2019-01-14 | 2019-01-14
Dashboard - Menu Items |  | Sub menu | Medium | 5 | Vishwanath M | 2019-01-15 | 2019-01-15
Dashboard - View More |  | Availed Leaves -View More (MoM trend chart) | Complex | 8 | Vishwanath M | 2019-01-15 | 2019-01-16
Dashboard - View More |  | Regularization -View More (MoM trend chart) | Medium | 5 | Vishwanath M | 2019-01-16 | 2019-01-17
Dashboard - View More |  | Learning Hours -View More (MoM trend chart) | Medium | 5 | Vishwanath M | 2019-01-17 | 2019-01-18
Dashboard - View More |  | Learning Hours -View More (Pending course) | Medium | 5 | Vishwanath M | 2019-01-21 | 2019-01-21
|  | End to End testing (Developer level Integration Testing) | Complex | 8 | Vishwanath M | 2018-01-22 | 2019-01-22
|  | Code Review | Complex | 8 | Vishwanath M | 2019-01-16 | 2019-01-22
|  | Merge, Fix Review Comments, Deploy | Complex | 8 | Vishwanath M | 2019-01-22 | 2019-01-23
|  | Fix Testing issues | Complex | 8 | Vishwanath M | 2019-01-24 | 2019-01-25
|  |  | Select | 0
EFFORT BREAK-UP |  |  |  | 91
11.375
|  |  |  | Select | 0
|  |  |  | Low | 2
|  |  |  | Simple | 3
|  |  |  | Medium | 5
|  |  |  | Complex | 8

## Angular
Effort Estimates (Man-hours)
USER STORY DECSRIPTION | JIRA ID | Front End | [5 empty] | Comments
|  | Components | Complexity | Effort (In Hrs) | Resource | Planned Start Date | Planned End Date
|  | Requirement Understanding, Analyze and Design the module . Do effort estimation, Technical Discussion & get Clarification. | Medium | 5 | Monika | 2019-01-09 | 2019-01-09
|  | Setup Initial Project and Branch, | Medium | 5 | Monika | 2019-01-09 | 2019-01-10
Dashboard - Home Page |  | Model Creation & Service Call | Medium | 5 | Monika | 2019-01-10 | 2019-01-10
Dashboard - Home Page |  | On click open HR Leave service | Simple | 3 | Monika | 2019-01-10 | 2019-01-10
Dashboard - Home Page |  | Pending Requests | Medium | 5 | Monika | 2019-01-11 | 2019-01-11
Dashboard - Home Page |  | Availed Leaves | Complex | 8 | Monika | 2019-01-14 | 2019-01-14
Dashboard - Home Page |  | Regularization | Medium | 5 | Monika | 2019-01-11 | 2019-01-11
Dashboard - Home Page |  | Learning Hours | Medium | 5 | Monika | 2019-01-14 | 2019-01-14
Dashboard - Home Page |  | R-Samman | Simple | 3 | Monika | 2019-01-14 | 2019-01-14
Dashboard -Menu Items |  | Sub menu | Complex | 8 | Monika | 2018-01-15 | 2018-01-16
Dashboard - View More |  | Availed Leaves -View More (MoM trend chart) | Complex | 8 | Monika | 2018-01-16 | 2018-01-17
Dashboard - View More |  | Regularization -View More (MoM trend chart) | Medium | 5 | Monika | 2018-01-18 | 2018-01-18
Dashboard - View More |  | Learning Hours -View More (MoM trend chart) | Medium | 5 | Monika | 2018-01-18 | 2018-01-21
Dashboard - View More |  | Learning Hours -View More (Pending course) | Complex | 8 | Monika | 2018-01-21 | 2018-01-22
|  | End to End testing (Developer level Integration Testing) | Medium | 5 | Monika | 2018-01-22 | 2019-01-22
|  | Code Review | Medium | 5 | Monika | 2019-01-16 | 2019-01-22
|  | Merge, Fix Review Comments, Deploy | Simple | 3 | Monika | 2019-01-22 | 2019-01-23
|  | Fix Testing issues | Low | 2 | Monika | 2019-01-24 | 2019-01-25
|  |  | Select | 0
EFFORT BREAK-UP |  |  |  | 93
11.625
|  |  |  | Select | 0
|  |  |  | Low | 2
|  |  |  | Simple | 3
|  |  |  | Medium | 5
|  |  |  | Complex | 8

## Backend
Effort Estimates (Man-hours)
USER STORY DECSRIPTION | JIRA ID | Backend | [5 empty] | Comments
|  | Components/Operations/Transaction | Complexity | Effort (In Hrs) | Resource | Planned Start Date | Planned End Date
|  | Requirement Understanding, Analyze and Design the module . Do effort estimation, Technical Discussion & get Clarification. | Complex | 8 | Sanjay | 2019-01-09 | 2019-01-09
|  |  | Complex | 8 | Tarun | 2019-01-09 | 2019-01-09
|  | Setup Initial Project and Branch, | Low | 2 | Tarun | 2019-01-10 | 2019-01-10
Dashboard Menu |  | BE - Write Repository & Model | Low | 2 | Tarun | 2019-01-10 | 2019-01-10
Dashboard Menu |  | BE - Write API | Medium | 5 | Tarun | 2019-01-10 | 2019-01-10
My Pending Request |  | BE - Write Repository & Model | Low | 2 | Tarun | 2019-01-11 | 2019-01-11
My Pending Request |  | BE - Write API | Low | 2 | Tarun | 2019-01-11 | 2019-01-11
|  | Changes as per HANA view | Medium | 5 | Tarun | 2019-01-14 | 2019-01-14
|  | End to End testing (Developer level Integration Testing) | Complex | 8 | Tarun | 2018-01-22 | 2019-01-22
|  | Code Review | Simple | 3 | Sanjay | 2019-01-10 | 2019-01-16
|  | Merge, Fix Review Comments, Deploy | Low | 2 | Tarun | 2019-01-22 | 2019-01-23
|  | Fix Testing Issues | Simple | 3 | Tarun | 2019-01-24 | 2019-01-25
|  | Document API, Odata Inventory. Add Elastic Search JSON for Service | Simple | 3 | Tarun | 2019-01-11 | 2019-01-11
|  |  | Select | 0 | Tarun
EFFORT BREAK-UP |  |  |  | 53
6.625
|  |  |  | Select | 0
|  |  |  | Low | 2
|  |  |  | Simple | 3
|  |  |  | Medium | 5
|  |  |  | Complex | 8

## Testing
Effort Estimates (Man-hours)
USER STORY DECSRIPTION | JIRA ID | Testing | [5 empty] | Comments
|  | Feature/Test cases | Complexity | Effort (In Hrs) | Resource | Planned Start Date | Planned End Date
|  | Requirement Understanding, Analyze and Design the module . Do effort estimation, Technical Discussion & get Clarification. | Medium | 5 | Swati M | 2019-01-09 | 2019-01-09
Dashboard - Home Page |  | Write Test Case | Low | 2 | Swati M | 2019-01-15 | 2019-01-15
Dashboard - Home Page |  | Write Test Case | Low | 2 | Swati M | 2019-01-16 | 2019-01-16
Dashboard - Home Page |  | Write Test Case | Low | 2 | Swati M | 2019-01-17 | 2019-01-17
Dashboard - Home Page |  | Write Test Case | Low | 2 | Swati M | 2019-01-17 | 2019-01-17
Dashboard - Home Page |  | Write Test Case | Low | 2 | Swati M | 2019-01-18 | 2019-01-18
Dashboard - Home Page |  | Write Test Case | Low | 2 | Swati M | 2019-01-18 | 2019-01-18
Dashboard - Menu Items |  | Write Test Case | Low | 2 | Swati M | 2019-01-18 | 2019-01-18
Dashboard - View More |  | Write Test Case | Low | 2 | Swati M | 2019-01-21 | 2019-01-21
Dashboard - View More |  | Write Test Case | Low | 2 | Swati M | 2019-01-21 | 2019-01-21
Dashboard - View More |  | Write Test Case | Low | 2 | Swati M | 2019-01-21 | 2019-01-21
|  | Prepare/Get Test Data | Complex | 8 | Swati M | 2019-01-22 | 2019-01-23
|  | End to end testing flow in Ipad or android | Complex | 8 | Swati M | 2019-01-24 | 2019-01-24
|  |  | Complex | 8 | Swati M | 2019-01-25 | 2019-01-25
|  |  | Select | 0
EFFORT BREAK-UP |  |  |  | 49
6.125
|  |  |  | Select | 0
|  |  |  | Low | 2
|  |  |  | Simple | 3
|  |  |  | Medium | 5
|  |  |  | Complex | 8

## Assumption
USER STORY DECSRIPTION | JIRA ID | Assumption
All | All | External API details should be available
HANA View should be available
Column Mapping should be available
Proper Data will be available to test the Chart Views in Dev, QA, UAT.

## Guideline
Guideline for Estimates
1 | To estimate the Development effort which will cover only development + unit testing + Review
2 | Defect fixing Time will be allocated separately.
3 | Defect fixing Time should not be more than 10% of Development Time
4 | Any functional changes after estimates will be considered as CR. CT will be accommodated by extending given estimates and end date. | Table-A
5 | Provide assumption(Refer Assumption Sheet) if any considered or anticipated during estimates | Low | 2
6 | Effort will be calculated based on selected complexity (Refer Table-A). If Any Task is very complex which is required more affort then break down further into any of given complexity | Simple | 3
|  | Medium | 5
|  | Complex | 8

## Sprint # 10 - Details (hidden)
2-Week Sprint | Date | Total Days
Sprint Start Date | 2018-07-09 | 13
Sprint End Date | 2018-07-25
Resource Skills | Count | Planned Effort (Hrs) ** | Available Effort (Hrs) **
HTML Resources | 2 | 208 | 188
Frontend Resources | 2 | 208 | 188
Backend Resources | 3 | 312 | 282
Testing Resources | 1 | 104 | 94
Total Resources | 8 | 832 | 752
** 8-Hour working considered per day
Sprint Ceremonies & Other Activities (All Resources) | Std Effort (Hrs) | Overall Effort (Hrs) | HTML | FE | BE | TESTING
Sprint Planning Sessions | 2 | 16 | 4 | 4 | 6 | 2
Daily Stand-up Calls | 0.5 | 40 | 10 | 10 | 15 | 5
Product Backlog Refinement Session | 2 | 16 | 4 | 4 | 6 | 2
Sprint Review Sessions | 0 | 0 | 0 | 0 | 0 | 0
Sprint Retrospective Sessions | 1 | 8 | 2 | 2 | 3 | 1
Vacation Plans & Holiday |  | 0 | 0 | 0 | 0 | 0
Total Additional Efforts |  | 80 | 20 | 20 | 30 | 10
Available Capacity for Completing Sprint Stories - FINAL [Rounded] |  | 752 | 188 | 188 | 282 | 94
Effort Required for completing all stories |  | #REF! | #REF! | #REF! | #REF! | #REF!
Capacity Utilized (in %) |  | #REF! | #REF! | #REF! | #REF! | #REF!
Unutilized Capacity (in Hrs) |  | #REF! | #REF! | #REF! | #REF! | #REF!
Unutilized Capacity (in %) |  | #REF! | #REF! | #REF! | #REF! | #REF!
Note on B26: Refer to "Resource & Vacation Details" tab for details

## Resource & Vacation Details (hidden)
[14 empty] | Complexity | Low | Medium | Complex | Very Complex
[14 empty] | Hours | 3 | 6 | 8 | 16
| Sprint Start Date | 2018-07-09
| Sprint End Date | 2018-07-25
| Total Days | 13
| RIL Holiday | 0
| Business Hours Per Day | 8
SNO | Resource Name | Tech Skill | Resource/Effort Availability | [6 empty] | Vacation Plan |  |  | Stand-up Calls Attendance
|  |  | Vacation (Business Days) | Vacation (in hrs) | Holiday (in hrs) | Available Man Days | Total Hours | Available Hours | % Allocation | From Date | To Date | Comments
1 | Shaqeel | HTML | 0 | 0 | 0 | 13 | 104 | 104 | 100%
2 | Priyanka | HTML | 0 | 0 | 0 | 13 | 104 | 104 | 100%
2 |  |  | 0 | 0 | 0 | 26 | 208 | 208
1 | Bhushan | FrontEnd | 0 | 0 | 0 | 13 | 104 | 104 | 100%
2 | Tabish | FrontEnd | 0 | 0 | 0 | 13 | 104 | 104 | 100%
2 |  |  | 0 | 0 | 0 | 26 | 208 | 208
1 | Anshul J | Backend | 0 | 0 | 0 | 13 | 104 | 104 | 100%
2 | Divyesh.P | Backend | 0 | 0 | 0 | 13 | 104 | 104 | 100%
3 | Sanjay | Backend | 0 | 0 | 0 | 13 | 104 | 104 | 100%
3 |  |  | 0 | 0 | 0 | 39 | 312 | 312
1 | Sapna | TESTING | 0 | 0 | 0 | 13 | 104 | 104 | 100%
1 |  |  | 0 | 0 | 0 | 13 | 104 | 104
8 |  |  | 0 | 0 | 0 | 104 | 832 | 832
Total Hours Lost (Vacations + Holidays) |  |  | 0
Formulas:
Resource/Effort Availability = NETWORKDAYS([Vacation Plan],[To Date])

## Points Table (hidden)
Start Range (Hrs) | End Range (Hrs) | Incremental Value | Story Point
0 | 4 | 4 | 1
5 | 12 | 8 | 2
13 | 24 | 12 | 3
25 | 44 | 20 | 5
45 | 76 | 32 | 8
77 | 121 | 45 | 13
122 | 181 | 60 | 21
182 | 261 | 80 | 34
262 | 371 | 110 | 55